	Phases
	Tasks
	Dates

	
Introduction


	Prepare the equipment
	9-10 February, 2015

	
	Filming
	11-12 February, 2015

	
	Editing
	16-21 February, 2015

	
	Submission
	23 February, 2015

	






Research


	Research on following topic 
· Cultural Significance
· Why it has been influential?
· Theme that will tie all the examples and topics together
· Common misunderstanding/misconception about the one thousand and one nights
· The actual facts about one thousand and one nights
· Relevant and interesting examples



	




13-24 February, 2015 

	



Brainstorm


	Brainstorm on following discussion
· Selecting the most relevant and interesting theme, misconception, misunderstanding and facts from the researches
· Creative ways to present the information and engage the audiences
· How should story flow? (From start to the end) 
· Settings of the each scene (locations, angle, timing, lighting, technique etc.) 
· Dialogs and actions

	






25 February – 4 March, 2015
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	Phases
	Tasks
	Dates

	





Screenplay

	Start writing screenplay from the brainstormed information
· Settings
· Actions
· Dialogs
· Narration

	


4-9 March, 2015

	
	Check the screenplay by asking reputable sources such as librarian, professors or those who have vast knowledge about this book for opinion.
	
10 March, 2015

	
	Finalise the screen play

	11-15 March, 2016

	
	Submission
	16 March, 2015

	


Filming


	Starting filming according to the screenplay scene by scene
	17–27 March, 2015

	
	Review by Director
Get advice from film expert (if possible)
	28-30 March, 2015

	
	Adjust and retake
	31 March–2 April, 2015

	

Editing

	Start editing and add subtitle
	2-12 April, 2015

	
	Review by friends, professors, TA, those who have read the books
	16-17 April, 2015

	
	Improve the documentary video according to the comments
	17-21 April, 2015

	
Transcript

	
Write and complete the transcript
	
21-24 April, 2015

	
Upload

	
Upload video to YouTube and send the link to Aj. Russell
	
26 April, 2015













	Name / Student ID
	 Roles / Contributions

	Tassanapol Sa-ngumram (Benz) 5704642759
	Script writer, Editor, Co-director, Researcher

	Sakonwat Apiwattanawong (Pao) 5704641959
	Executive Producer, Researcher

	Thanyapat Jureekittiyakul (Mine) 5704642395
	Actress, Transcript writer, Researcher

	Poomthanik Kamonwat (Poom) 5704641819
	Director, Cinematographer, Script writer, Researcher

	Pongsakorn Preteepsritorn (Plane) 5704641793
	Editor, Adding subtitles, Transcript writer, Researcher

	Widhit Xuto (In) 5704642593
	Actor, Transcript writer, Researcher

	Phongporn Nitisahakul (Moouan) 5704641678
	Cinematographer, Actor, Researcher

	Woraphong Chaisereelamlert (tee) 5704642635
	[bookmark: _GoBack]Cinematographer, Editor, Researcher 
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