| Phases | Tasks | Dates |
| --- | --- | --- |
| Introduction | Prepare the equipment | 9-10 February, 2015 |
|  | Filming | 11-12 February, 2015 |
|  | Editing | 16-21 February, 2015 |
|  | Submission | 23 February, 2015 |
| Research | Research on following topic - Cultural Significance - Why it has been influential? - Theme that will tie all the examples and topics together - Common misunderstanding/misconception about the one thousand and one nights - The actual facts about one thousand and one nights - Relevant and interesting examples | 13-24 February, 2015 |
| Brainstorm | Brainstorm on following discussion - Selecting the most relevant and interesting theme, misconception, misunderstanding and facts from the researches - Creative ways to present the information and engage the audiences - How should story flow? (From start to the end) - Settings of the each scene (locations, angle, timing, lighting, technique etc.) - Dialogs and actions | 25 February – 4 March, 2015 |

One thousand and one nights project plan

| Phases | Tasks | Dates |
| --- | --- | --- |
| Screenplay | Start writing screenplay from the brainstormed information - Settings - Actions - Dialogs - Narration | 4-9 March, 2015 |
|  | Check the screenplay by asking reputable sources such as librarian, professors or those who have vast knowledge about this book for opinion. | 10 March, 2015 |
|  | Finalise the screen play | 11-15 March, 2016 |
|  | Submission | 16 March, 2015 |
| Filming | Starting filming according to the screenplay scene by scene | 17–27 March, 2015 |
|  | Review by Director Get advice from film expert (if possible) | 28-30 March, 2015 |
|  | Adjust and retake | 31 March–2 April, 2015 |
| Editing | Start editing and add subtitle | 2-12 April, 2015 |
|  | Review by friends, professors, TA, those who have read the books | 16-17 April, 2015 |
|  | Improve the documentary video according to the comments | 17-21 April, 2015 |
| Transcript | Write and complete the transcript | 21-24 April, 2015 |
| Upload | Upload video to YouTube and send the link to Aj. Russell | 26 April, 2015 |

| Name / Student ID | Roles / Contributions |
| --- | --- |
| Tassanapol Sa-ngumram (Benz) 5704642759 | Script writer, Editor, Co-director, Researcher |
| Sakonwat Apiwattanawong (Pao) 5704641959 | Executive Producer, Researcher |
| Thanyapat Jureekittiyakul (Mine) 5704642395 | Actress, Transcript writer, Researcher |
| Poomthanik Kamonwat (Poom) 5704641819 | Director, Cinematographer, Script writer, Researcher |
| Pongsakorn Preteepsritorn (Plane) 5704641793 | Editor, Adding subtitles, Transcript writer, Researcher |
| Widhit Xuto (In) 5704642593 | Actor, Transcript writer, Researcher |
| Phongporn Nitisahakul (Moouan) 5704641678 | Cinematographer, Actor, Researcher |
| Woraphong Chaisereelamlert (tee) 5704642635 | Cinematographer, Editor, Researcher |