Gulliver travel

13 Febuary : Our group will discuss about movie that we get “Gulliver travel” and find interesting content in the movie.

20 Febuary : This week ,we will brainstorming to find what effect and what graphic that we will use.

21-25 Febuary : At this period,we will meet our group at some place that we can make a shrort practice movie.

26-28 Febuary : At this period,we will use programe editor to décor short movie.

15-20 March : We will  meet our group and draw written plan for screenplay.

25-30 March : At this period,we will brainstorming to find effect that make our movie more interesting , find how to make fantastic sound  and survey the location that we will make a movies.

5-10 April : At this period, we will make a movies that we plan earlier.

12-25 April : At this period, we will use programe editor to edit our movie. At this process we will review everything that we miss and also add subtitle.

25 April : We expect that everything will be complete within this day.

1. Hugo :  This person will be the person that manage time, arrange an appointment and contact to everyone that relate to this project

2. Bank  :  This person will be photographer, he relate to everything about equipment that we will use in the movie.

3. Earth  :  This person will be director, he relate to screenplay and he is the main person that will find interesting effect and sound.

4. Sun  :  This person will relate to graphic and technic, he will use computer or electronic device to make film more interesting.

5. Keng  : This person will be co-director, he will assist director to achieve our ideal screenplay.

6. No :  This person will be assist person who do about graphic and technic and also assist other people in the group.