Lolita (Wednesday Class)

Name				Nickname   		Student ID  		             Position

1. Yada Todsathamseth		   Nam 			5704642668                                    Writer
2. Suthinee Katakhunpisarn 	    C 			5704642221		       Editor/Director
3. Sittijet Inthachak 		    Sun			5704642056                         Cinematographer
4. Patsanut Klaitae 		   Tarn 			5704641561                                    Writer
5. Piyathida Rattanasuwan          Marmeaw 		5704641769                                   Actress
6. Peerada Kusumpanya                  Pear			5704641603                         Cinematographer/ Actress
7. Nannapat Vorayotsri                  Cartoon		5704642726                   Actress/Executive Producer
8. Phatarakorn Thongsathit          Graphic		5704641629                          Cinematographer
9. Roryol Chenaksara 		    Pam 			5704641926                                     Editor
10. Rawisara Thepthinnakorn       Cartoon 		5704641918                                     Actress

| Date | Activity |
| --- | --- |
| 4/2/15 | - Take the group picture - Group planning and assigning the work to each members - Position and jobs listed above |
| 11/2/15 | - Each member have to finish watching the movie Lolita and also understand the story either by reading the whole text or the summary in detailed. - Meet up and discuss which perspective and interesting points of the story that will be put in the documentary. |
| 18/2/15 | - After listed the topics that is going to be in the documentary, each member must help in researching for the information about the topic they will be assigned. The compiled information must be send to Nam and Tarn for the screen play. - Plan together for the ideas of how to film and think of how to create creative video. - The script and the screenplay will be written by Tarn and Nam together. |
| 25/2/15 | - Proofread the screenplay - Find the appropriate location that can be used to film our documentary. - Contact the location for permission. |
| 4/3/15 | Since this week is the midterm exam week, we will not be able to do much work. Our plan is to keep track with our group members and their works and also the location that we have contacted. |
| 11/3/15 | - Start filming for the documentary - Finding background music for each of the scenes |
| 25/3/15 | - Continue Filming - |
| 1/4/15 | - Start editing by C and Pam - Film for more scenes if needed |
| 8/4/15 | - Continue Editing - |
| 15/4/15 | - Putting Subtitle - Making Transcript |
| 22/4/15 | - Final Editing - |

Timetable

Note: Cartoon (Nannapat) will be keeping track of each member works and make sure the plan is going well.