Group Project Plan Due - “Alice’s adventure in Wonderland”

| Date | Phases | Tasks |
| --- | --- | --- |
| 3 February 2015 |  | Group planning #1 (Introduction movie) |
| 6-7 February 2015 |  | Declare work & Prepare equipment |
|  | Introduction |  |
| 10-12 February 2015 |  | Filming |
| 13-16 February 2015 |  | Editing |
| 17-19 February 2015 |  | Checking |
| 23 February 2015 |  | Submission |
|  | Research |  |
| 26-27 February 2015 |  | Group planning #2 (Movie) |
| 29 Feb - 8 Mar 2015 |  | Researching - Framework - Analyzing information from novel and movie - Approving by feedback |
|  | Brainstorm |  |
| 9 March 2015 |  | - Detailed & analyze all information - Compare differences from novel and movie - Selecting an interesting scenes & the climax of the story - Planning on the filming process - Scene setting (location, detail, angles, timing, technique) |
|  | Screenplay |  |
| 10-11 March 2015 |  | Writing screenplay from brainstormed information - Dialogs - Setting - Scenes - Actions - Narration |
| 12-14 March 2015 |  | Verification the screenplay |
| 16 March 2015 |  | Submission |
|  | Filming |  |
| 18-24 March 2015 |  | Filming according to the previous screenplay |
| 25-26 March 2015 |  | Retake and adjust some mistake |
|  | Editing |  |
| 27 March - 2 April 2015 |  | Editing |
| 3-6 April 2015 |  | Adding subtitle |
| 7-11 April 2015 |  | Fixing common sound problem and getting feedback |
| 17-20 April 2015 |  | Review by professors and expertise |
|  | Transcript |  |
| 21-24 April 2015 |  | Write and complete the transcript |
| 26 April 2015 | Upload | Upload video to YouTube and send link to Dr. Russell Jones |

Member list & position

Thanunpatch  Rumakom (Prae)	 	5704642387	Cinematographer , Editor

Phimkan 	Taesakun  (Pim)		5704641660	Editor, Director

Pajaree	Khampor  (Pang)		5704641405	Actress, Writer

Thawanhatai	Kruayatidee (Cindy)		5704642403	Writer, Actress

Pittayarat	Thanusuwannasak  (Nice)	5704641751	Actress, Writer

Waranda	Saengmuenpetch (Oum)	5704642554	Director, EP